Walmart

MEMORANDUM
To: 	Lee Scott, CEO
From: 	Glenn Frey, Don Henley, Joe Walsh, and Timothy B. Schmit, Eagles
Date: 	May 1, 2007
Re: 	SCOPE OF WORK AND TIMELINE FOR NEW EAGLES ALBUM

The information provided below explains the scope of the work and the timeline for the completion of the album Long Road Out of Eden.  The album will be ready for the post-production process by July 31, 2008.

Scope of the Work
The songwriting and initial arrangements are complete.  Demos have been recorded. We have picked a single for release. We still need to finish recording the music and vocals for the tracks, as well as complete mixing.

Recording
The Eagles wish to lay down their vocals and instrumentation separately in the studio.  Glenn Frey will lay down his vocals from May 2-May 9. Don Henley will record his vocal tracks from May 10-May 20. Joe Walsh will come into the studio daily from May 21-May 30 in order to lay down his guitar tracks. Timothy B. Schmit will come into the studio daily to record his bass tracks from June 2-June 7.  From June 8-June 18, the following musicians will come in and fill out the sound: Steuart Smith: guitar, keyboards; Scott Crago: drums; Richard Davis: keyboards; Michael Thompson: keyboards; Will Hollis: keyboards; Al Garth: alto sax and violin; Bill Armstrong: trumpet; Chris Mostert: tenor and alto sax; Greg Smith: baritone sax; Greg Leisz: pedal steel; Lenny Castro: percussion; Luis Conti: percussion.

Mixing
Glenn Frey and Richard Davis will handle all orchestration mixing and arrangements from June 19-June 26. Don Henley and Greg Smith will handle all mixing and arrangement of horns during that same time period. Frey and Davis will be working in Frey’s home studio; Henley and Smith will be working in Henley’s home studio. They will e-mail MP3s of the arrangements to each other before any mixing decisions are made.  Elliott Scheiner will finalize the mixing at the Doghouse Studio in Los Angeles from June 27-July 10.

Finalization
The Eagles as a group will review the tracks before submitting them to the company. This review process, as well as fixing any problems and making pertinent changes, should take no longer than two weeks (July 11-July 25).

Timeline
The following table shows the timeline and delegation of tasks.

| Tasks to be Completed | Responsible Persons | Completion Dates |
| --- | --- | --- |
| Recording of vocals | Glenn Frey | May 2 – May 9 |
| Recording of vocals | Don Henley | May 10 – May 20 |
| Recording of guitar tracks | Joe Walsh | May 21 – May 30 |
| Recording of bass tracks | Timothy B. Schmit | June 2 – June 7 |
| Recording of additional guitar tracks | Steuart Smith | June 8 – June 9 |
| Recording of drums and percussion | Scott Crago, Lenny Castro, Luis Conti | June 10 – June 12 |
| Recording of keyboards | Richard Davis, Michael Thompson, Will Hollis, Steuart Smith | June 14 – June 15 |
| Recording of horns | Al Garth, Bill Armstrong, Chris Mostert, Greg Smith | June 16 – June 17 |
| Recording of pedal steel | Greg Leisz | June 18 |
| Mixing/arranging of orchestration | Glenn Frey, Richard Davis | June 19 – June 26 |
| Mixing/arranging of horns | Don Henley, Greg Smith | June 19 – June 26 |
| Finalization of mixing | Elliott Scheiner | June 27 – July 10 |
| Review and repair | Eagles Group | July 11 – July 25 |
| Submission of product | Eagles Group | July 31 |

Album Will Be Ready by August
We fully expect the completion of the album in time for an August 31 release of the first single, which we have determined to be “How Long.” If you have any questions, please feel free to contact us at eaglesonlinecentral@gmail.com.